## General test Plan
Project name | CALIFORNIA MARKETING
Website | https://qasvus.wixsite.com/ca-marketing
Prepared by | Elena Solgunova
Date | 10/21/2021
TEST PLAN
1. Introduction
2.Scope
3. Quality Objectives
4. Test Approach
5. Entry and Exit Criteria
6. Suspension Criteria and Resumption Requirements
7. Test Strategy
8. Resource and Environment needs
INTRODUCTION
The Test Plan has been created to communicate the test approach to team members. It includes the objectives, scope, schedule, risks and approach. This document will clearly identify what the test deliverables will be and what is deemed in and out of scope.
SCOPE
The document mainly targets the Manual test, Automation test, API test, Performance Automation test, and validating data in report output as per Requirements Specifications provided by Client.
QUALITY OBJECTIVES
A primary objective of testing is to: assure that the system meets the full requirements, including quality requirements (functional and non-functional requirements) and fit metrics for each quality requirement and satisfies the use case scenarios and maintain the quality of the product. The secondary objectives of testing will be to identify and expose all issues and associated risks, communicate all known issues to the project team, and ensure that all issues are addressed in an appropriate matter before release.
TEST APPROACH
Analytical test approach was used, in accordance to requirements-based strategy, where an analysis of the requirements’ specification form is the basis for planning,estimating and designing tests. Test cases will be created during exploratory testing. All project is using an Agile approach, with weekly iterations. At the end of each week the requirements identified for that iteration will be delivered to the team and will be tested.
ENTRY AND EXIT CRITERIA
Entry Criteria: - proper test data should be availble - all the necessary documentation, design, and requirements information should be available that will allow testers to operate the system and judge the correct behavior. - all the standard software tools including the testing tools must have been successfully installed and functioning properly. - all test hardware platforms must have been successfully installed, configured, and functioning properly.
Exit Criteria: - no high priority or severe bugs are left outstanding. - a certain level of requirements coverage has been achieved. - all high-risk areas have been fully tested, with only minor residual risks left outstanding. - the schedule has been achieved.
SUSPENSION CRITERIA AND RESUMPTION REQUIREMENTS
Suspension criteria - Software/Hardware problems. - Significant change in requirements suggested by client. - The build contains many serious defects which seriously or limit testing progress. - Assigned resources are not available when needed by test team.
Resumption criteria - Resumption will only occur when the problem that caused the suspension has been resolved.
TEST STRATEGY
QA role in test process: - Understanding Requirements. - Requirement specifications will be sent by client
Preparing Test Cases: - QA will be preparing test cases based on the exploratory testing. This will cover all scenarios for requirements.
Preparing Test Matrix: - QA will be preparing test matrix which maps test cases to respective requirement. This will ensure the coverage for requirements.
Reviewing test cases and matrix: - Review for test cases and test matrix will be conducted by QA Lead. - Any comments or suggestions on test cases and test coverage will be provided by reviewer - Suggestions or improvements will be updated by preparer and sent to QA Lead for approval. - Updates and improvements will be reviewed and approved by reviewer.
Creating Test Data: - Test data will be created by respective QA based on scenarios and Test cases.
Executing Test Cases: - Test cases will be executed by respective QA based on designed scenarios, test cases and Test data. - Test result (Actual Result, Pass/Fail) will be updated in test case document Defect Logging and Reporting: QA will be logging the defect/bugs in Excel spreadsheet and JIRA, found during execution of test cases.
Retesting and Regression Testing: - Retesting for fixed bugs will be done by respective QA once issue is resolved by respective developer and bug/defect status will be updated accordingly. In certain cases, regression testing will be done if required.
Deployment/Delivery: - Once all bugs/defect reported after complete testing is fixed and no other bugs are found,report will be deployed to the client, along with sample output by email to respective lead and Report group
RESOURCE AND ENVIRONMENT NEEDS
PC OS: Windows 10 Home 64 bit Operation System Browser: Chrome 92

## Manual Test Plan
Project name | CALIFORNIA MARKETING
Website | https://qasvus.wixsite.com/ca-marketing
Prepared by | Elena Solgunova
Date | 10/21/2021
TEST PLAN
1. Introduction
2.Scope
3. Quality Objectives
4. Test Approach
5. Entry and Exit Criteria
6. Suspension Criteria and Resumption Requirements
7. Test Strategy
8. Resource and Environment needs
INTRODUCTION
The Test Plan has been created to communicate the test approach to team members. It includes the objectives, scope, schedule, risks and approach. This document will clearly identify what the test deliverables will be and what is deemed in and out of scope.
SCOPE
The document mainly targets the Manual testing, including Positive and Negative testing, GUI testing, and validating data in report output as per Requirements Specifications provided by Client.
QUALITY OBJECTIVES
A primary objective of testing is to: assure that the system meets the full requirements, including quality requirements (functional and non-functional requirements) and fit metrics for each quality requirement and satisfies the use case scenarios and maintain the quality of the product. The secondary objectives of testing will be to identify and expose all issues and associated risks, communicate all known issues to the project team, and ensure that all issues are addressed in an appropriate matter before release.
TEST APPROACH
Analytical test approach was used, in accordance to requirements-based strategy, where an analysis of the requirements’ specification form is the basis for planning,estimating and designing tests. Test cases will be created during exploratory testing. All project is using an Agile approach, with weekly iterations. At the end of each week the requirements identified for that iteration will be delivered to the team and will be tested.
ENTRY AND EXIT CRITERIA
Entry Criteria: - proper test data should be availble - all the necessary documentation, design, and requirements information should be available that will allow testers to operate the system and judge the correct behavior. - all the standard software tools including the testing tools must have been successfully installed and functioning properly. - all test hardware platforms must have been successfully installed, configured, and functioning properly.
Exit Criteria: - no high priority or severe bugs are left outstanding. - a certain level of requirements coverage has been achieved. - all high-risk areas have been fully tested, with only minor residual risks left outstanding. - the schedule has been achieved.
SUSPENSION CRITERIA AND RESUMPTION REQUIREMENTS
Suspension criteria - Software/Hardware problems. - Significant change in requirements suggested by client. - The build contains many serious defects which seriously or limit testing progress. - Assigned resources are not available when needed by test team.
Resumption criteria - Resumption will only occur when the problem that caused the suspension has been resolved.
TEST STRATEGY
QA role in test process: - Understanding Requirements. - Requirement specifications will be sent by client
Preparing Test Cases: - QA will be preparing test cases based on the exploratory testing. This will cover all scenarios for requirements.
Preparing Test Matrix: - QA will be preparing test matrix which maps test cases to respective requirement. This will ensure the coverage for requirements.
Reviewing test cases and matrix: - Review for test cases and test matrix will be conducted by QA Lead. - Any comments or suggestions on test cases and test coverage will be provided by reviewer - Suggestions or improvements will be updated by preparer and sent to QA Lead for approval. - Updates and improvements will be reviewed and approved by reviewer.
Creating Test Data: - Test data will be created by respective QA based on scenarios and Test cases.
Executing Test Cases: - Test cases will be executed by respective QA based on designed scenarios, test cases and Test data. - Test result (Actual Result, Pass/Fail) will be updated in test case document Defect Logging and Reporting: QA will be logging the defect/bugs in Excel spreadsheet and JIRA, found during execution of test cases.
Retesting and Regression Testing: - Retesting for fixed bugs will be done by respective QA once issue is resolved by respective developer and bug/defect status will be updated accordingly. In certain cases, regression testing will be done if required.
Deployment/Delivery: - Once all bugs/defect reported after complete testing is fixed and no other bugs are found,report will be deployed to the client, along with sample output by email to respective lead and Report group
RESOURCE AND ENVIRONMENT NEEDS
PC OS: Windows 10 Home 64 bit Operation System Browser: Chrome 92

## Automation test Plan
Project name | CALIFORNIA MARKETING
Website | https://qasvus.wixsite.com/ca-marketing
Prepared by | Elena Solgunova
Date | 10/21/2021
TEST PLAN
1. Introduction
2.Scope
3. Quality Objectives
4. Test Approach
5. Entry and Exit Criteria
6. Suspension Criteria and Resumption Requirements
7. Test Strategy
8. Resource and Environment needs
INTRODUCTION
The Test Plan has been created to communicate the test approach to team members. It includes the objectives, scope, schedule, risks and approach. This document will clearly identify what the test deliverables will be and what is deemed in and out of scope.
SCOPE
The document mainly targets the Automation testing (from manual test plan) using Selenium IDE tool.
QUALITY OBJECTIVES
A primary objective of testing is to: assure that the system meets the full requirements, including quality requirements (functional and non-functional requirements) and fit metrics for each quality requirement and satisfies the use case scenarios and maintain the quality of the product. The secondary objectives of testing will be to identify and expose all issues and associated risks, communicate all known issues to the project team, and ensure that all issues are addressed in an appropriate matter before release.
TEST APPROACH
Analytical test approach was used, in accordance to requirements-based strategy, where an analysis of the requirements’ specification form is the basis for planning,estimating and designing tests. Test cases will be created during exploratory testing. All project is using an Agile approach, with weekly iterations. At the end of each week the requirements identified for that iteration will be delivered to the team and will be tested.
ENTRY AND EXIT CRITERIA
Entry Criteria: - proper test data should be availble - all the necessary documentation, design, and requirements information should be available that will allow testers to operate the system and judge the correct behavior. - all the standard software tools including the testing tools must have been successfully installed and functioning properly. - all test hardware platforms must have been successfully installed, configured, and functioning properly.
Exit Criteria: - no high priority or severe bugs are left outstanding. - a certain level of requirements coverage has been achieved. - all high-risk areas have been fully tested, with only minor residual risks left outstanding. - the schedule has been achieved.
SUSPENSION CRITERIA AND RESUMPTION REQUIREMENTS
Suspension criteria - Software/Hardware problems. - Significant change in requirements suggested by client. - The build contains many serious defects which seriously or limit testing progress. - Assigned resources are not available when needed by test team.
Resumption criteria - Resumption will only occur when the problem that caused the suspension has been resolved.
TEST STRATEGY
QA role in test process: - Understanding Requirements. - Requirement specifications will be sent by client
Preparing Test Cases: - QA will be preparing test cases based on the exploratory testing. This will cover all scenarios for requirements.
Preparing Test Matrix: - QA will be preparing test matrix which maps test cases to respective requirement. This will ensure the coverage for requirements.
Reviewing test cases and matrix: - Review for test cases and test matrix will be conducted by QA Lead. - Any comments or suggestions on test cases and test coverage will be provided by reviewer - Suggestions or improvements will be updated by preparer and sent to QA Lead for approval. - Updates and improvements will be reviewed and approved by reviewer.
Creating Test Data: - Test data will be created by respective QA based on scenarios and Test cases.
Executing Test Cases: - Test cases will be executed by respective QA based on designed scenarios, test cases and Test data. - Test result (Actual Result, Pass/Fail) will be updated in test case document Defect Logging and Reporting: QA will be logging the defect/bugs in Excel spreadsheet and JIRA, found during execution of test cases.
Retesting and Regression Testing: - Retesting for fixed bugs will be done by respective QA once issue is resolved by respective developer and bug/defect status will be updated accordingly. In certain cases, regression testing will be done if required.
Deployment/Delivery: - Once all bugs/defect reported after complete testing is fixed and no other bugs are found,report will be deployed to the client, along with sample output by email to respective lead and Report group
RESOURCE AND ENVIRONMENT NEEDS
PC OS: Windows 10 Home 64 bit Operation System Browser: Chrome 92

## API test plan
Project name | CALIFORNIA MARKETING
Website | https://qasvus.wixsite.com/ca-marketing
Prepared by | Elena Solgunova
Date | 10/21/2021
TEST PLAN
1. Introduction
2.Scope
3. Quality Objectives
4. Test Approach
5. Entry and Exit Criteria
6. Suspension Criteria and Resumption Requirements
7. Test Strategy
8. Resource and Environment needs
INTRODUCTION
The Test Plan has been created to communicate the test approach to team members. It includes the objectives, scope, schedule, risks and approach. This document will clearly identify what the test deliverables will be and what is deemed in and out of scope.
SCOPE
The document mainly targets the Manual API testing, using Postman API.
QUALITY OBJECTIVES
A primary objective of testing is to: assure that the system meets the full requirements, including quality requirements (functional and non-functional requirements) and fit metrics for each quality requirement and satisfies the use case scenarios and maintain the quality of the product. The secondary objectives of testing will be to identify and expose all issues and associated risks, communicate all known issues to the project team, and ensure that all issues are addressed in an appropriate matter before release.
TEST APPROACH
Analytical test approach was used, in accordance to requirements-based strategy, where an analysis of the requirements’ specification form is the basis for planning,estimating and designing tests. Test cases will be created during exploratory testing. All project is using an Agile approach, with weekly iterations. At the end of each week the requirements identified for that iteration will be delivered to the team and will be tested.
ENTRY AND EXIT CRITERIA
Entry Criteria: - proper test data should be availble - all the necessary documentation, design, and requirements information should be available that will allow testers to operate the system and judge the correct behavior. - all the standard software tools including the testing tools must have been successfully installed and functioning properly. - all test hardware platforms must have been successfully installed, configured, and functioning properly.
Exit Criteria: - no high priority or severe bugs are left outstanding. - a certain level of requirements coverage has been achieved. - all high-risk areas have been fully tested, with only minor residual risks left outstanding. - the schedule has been achieved.
SUSPENSION CRITERIA AND RESUMPTION REQUIREMENTS
Suspension criteria - Software/Hardware problems. - Significant change in requirements suggested by client. - The build contains many serious defects which seriously or limit testing progress. - Assigned resources are not available when needed by test team.
Resumption criteria - Resumption will only occur when the problem that caused the suspension has been resolved.
TEST STRATEGY
QA role in test process: - Understanding Requirements. - Requirement specifications will be sent by client
Preparing Test Cases: - QA will be preparing test cases based on the exploratory testing. This will cover all scenarios for requirements.
Preparing Test Matrix: - QA will be preparing test matrix which maps test cases to respective requirement. This will ensure the coverage for requirements.
Reviewing test cases and matrix: - Review for test cases and test matrix will be conducted by QA Lead. - Any comments or suggestions on test cases and test coverage will be provided by reviewer - Suggestions or improvements will be updated by preparer and sent to QA Lead for approval. - Updates and improvements will be reviewed and approved by reviewer.
Creating Test Data: - Test data will be created by respective QA based on scenarios and Test cases.
Executing Test Cases: - Test cases will be executed by respective QA based on designed scenarios, test cases and Test data. - Test result (Actual Result, Pass/Fail) will be updated in test case document Defect Logging and Reporting: QA will be logging the defect/bugs in Excel spreadsheet and JIRA, found during execution of test cases.
Retesting and Regression Testing: - Retesting for fixed bugs will be done by respective QA once issue is resolved by respective developer and bug/defect status will be updated accordingly. In certain cases, regression testing will be done if required.
Deployment/Delivery: - Once all bugs/defect reported after complete testing is fixed and no other bugs are found,report will be deployed to the client, along with sample output by email to respective lead and Report group
RESOURCE AND ENVIRONMENT NEEDS
PC OS: Windows 10 Home 64 bit Operation System Browser: Chrome 92